## EffortRawData
Project Name: | Ninniltoz |  |  | You do not need to edit yellow cells! |  |  |  | Entry hints in cells with red corners, just hover over cell.
Project Team Members: | Dustin Pernell | Jonah Ross
Effort per task in Week ENDING on identified dates
Current Week: | 2021-02-10
Totals: | 22 |  | 67 | 17.5 | 61.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5
Task | Date Added | GitHub Issue | Effort Estimate | Actual Effort | 2021-02-03 | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-03 | 2021-03-10 | 2021-03-17 | 2021-03-24 | 2021-03-31 | 2021-04-07 | 2021-04-14 | 2021-04-21 | 2021-04-28
Setup Site Ground | 2021-02-06 | #2 | 2 | 2 | 2021-02-03: 2
Create Base Page | 2021-02-06 | #4 | 4 | 2.5 | 2021-02-03: 2.5
Create Login Page (Full) | 2021-02-06 | #5 | 6 | 7 | 2021-02-10: 7
Admin Card Update Page Layout | 2021-02-06 | #20 | 2 | 0
Admin Card Update Page Functionality | 2021-02-06 | #21 | 10 | 5 | 2021-02-03: 1; 2021-02-10: 4
Admin Card Update Page Feature (Display update) | 2021-02-06 | #22 | 2 | 1 | bar: 2021-02-10
User Card Display Page Layout | 2021-02-06 | #11 | 2 | 0
User Card Display Page Fuctionality | 2021-02-06 | #12 | 4 | 0
Home Page Fuctionality | 2021-02-06 | #9 | 3 | 0
User Card Display Page Feature (Filter) | 2021-02-06 | #14 | 3 | 0
User Card Display Page Feature (Card Objects) | 2021-02-06 | #13 | 4 | 0
User Deck List Page Layout | 2021-02-06 | #15 | 2 | 0
User Deck List Page Fuctionality | 2021-02-06 | #16 | 4 | 0
User Deck Display Page Layout | 2021-02-06 | #17 | 2 | 0
User Deck Display Page Functionality | 2021-02-06 | #18 | 4 | 0
Home Page Layout | 2021-02-06 | #8 | 2 | 0
User Landing Page Layout | 2021-02-06 | #10 | 2 | 0
Admin Landing Page Layout | 2021-02-06 | #19 | 2 | 0
Develop Sitewide background | 2021-02-06 | #3 | 2 | 0
Create Logo | 2021-02-06 | #23 | 3 | 0
Login Page Bug (Layout) | 2021-02-06 | #6 | 1 | 0
Login Page Bug (Bad Creds) | 2021-02-06 | #7 | 1 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B1: Identify Project Name
Note on B2: Identify Project Originator
Note on C2: Identify Project Collaborator (if any)
Note on B4: Update to current "week ending" date
Note on A7: Break big issues into smaller (easier to estimate) "tasks"
Note on B7: Tracking date added let's us see when we identified specific work items. Good planning means less tasks added as project progresses.
Note on C7: Connects burndown task to github issue!
Note on D7: Best estimate in HOURS of how long to complete task. If having trouble, subdivide task more.
Note on F7: Enter HOURS (half hours can be .5) worked on task #1 in week ending 2/3/21
Note on G7: Enter HOURS worked (half hours can .5) on task #1 in week ending 2/10/21
Note on F25: Enter HOURS worked (half hours can be .5) on task #2 in week ending 2/3/21

## ChartData
DO NOT CHANGE ANYTHING IN THIS SHEET. IT AUTOMATICALLY PULLS DATA FROM THE 'EFFORT_RAW_DATA' SHEET.
Date | Me | Ideal | Forecast | Week
2021-02-03 | 67 | 67 | 67 | 1
2021-02-10 | 61.5 | 61.4167 | 61.5 | 2
2021-02-17 | 49.5 | 55.8333 | 49.5 | 3
2021-02-24 | 49.5 | 50.25 | 43.6667 | 4
2021-03-03 | 49.5 | 44.6667 | 37.8333 | 5
2021-03-10 | 49.5 | 39.0833 | 32 | 6
2021-03-17 | 49.5 | 33.5 | 26.1667 | 7
2021-03-24 | 49.5 | 27.9167 | 20.3333 | 8
2021-03-31 | 49.5 | 22.3333 | 14.5 | 9
2021-04-07 | 49.5 | 16.75 | 8.6667 | 10
2021-04-14 | 49.5 | 11.1667 | 2.8333 | 11
2021-04-21 | 49.5 | 5.5833 | 0 | 12
2021-04-28 | 49.5 | -8.8818e-15 | 0 | 13