## EffortRawData
Project Name: | Ninniltoz |  |  | You do not need to edit yellow cells! |  |  |  | Entry hints in cells with red corners, just hover over cell.
Project Team Members: | Dustin Pernell | Jonah Ross
Effort per task in Week ENDING on identified dates
Current Week: | 2021-02-17
Totals: | 20 |  | 106 | 41 | 100.5 | 87 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
Task | Date Added | GitHub Issue | Effort Estimate | Actual Effort | 2021-02-03 | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-03 | 2021-03-10 | 2021-03-17 | 2021-03-24 | 2021-03-31 | 2021-04-07 | 2021-04-14 | 2021-04-21 | 2021-04-28
Learn django | 2021-02-11 |  | 15 | 6 | 2021-02-17: 6
Setup local django env + 4 apps | 2021-02-11 |  | 2 | 2 | 2021-02-17: 2
Setup MySQL db instance | 2021-02-11 |  | 2 | 2 | 2021-02-17: 2
Create Login Page | 2021-02-11 |  | 4 | 4 | 2021-02-17: 4
Create Registration Page | 2021-02-12 |  | 2 | 2 | 2021-02-17: 2
Create base page | 2021-02-12 |  | 5 | 2 | 2021-02-17: 2
0
Admin Card Update Page Functionality | 2021-02-06 | #21 | 10 | 6.5 | 2021-02-03: 1; 2021-02-10: 5.5
Admin Card Update Page Feature (Display update) | 2021-02-06 | #22 | 2 | 1 | bar: 2021-02-10
User Card Display Page Fuctionality | 2021-02-06 | #12 | 9 | 0
Home Page Fuctionality | 2021-02-06 | #9 | 3 | 0
User Card Display Page Feature (Filter) | 2021-02-06 | #14 | 10 | 0
User Card Display Page Feature (Card Objects) | 2021-02-06 | #13 | 10 | 0
User Deck List Page Fuctionality | 2021-02-06 | #16 | 5 | 0
User Deck Display Page Functionality | 2021-02-06 | #18 | 10 | 0
Lifecounter (will be split up) | 2021-02-10 |  | 0 | 0
0
0
Setup Site Ground (SSG) | 2021-02-06 | #2 | 2 | 2 | 2021-02-03: 2
Create Base Page (SSG) | 2021-02-06 | #4 | 4 | 2.5 | 2021-02-03: 2.5
Create Login Page (Full) (SSG) | 2021-02-06 | #5 | 7 | 7 | 2021-02-10: 7
Discussed switching to django | 2021-02-10 |  | 2 | 2 | 2021-02-17: 2
Plan Lifecounter | 2021-02-10 |  | 2 | 2 | 2021-02-17: 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B1: Identify Project Name
Note on B2: Identify Project Originator
Note on C2: Identify Project Collaborator (if any)
Note on B4: Update to current "week ending" date
Note on A25: Break big issues into smaller (easier to estimate) "tasks"
Note on B25: Tracking date added let's us see when we identified specific work items. Good planning means less tasks added as project progresses.
Note on C25: Connects burndown task to github issue!
Note on D25: Best estimate in HOURS of how long to complete task. If having trouble, subdivide task more.
Note on F25: Enter HOURS (half hours can be .5) worked on task #1 in week ending 2/3/21
Note on G25: Enter HOURS worked (half hours can .5) on task #1 in week ending 2/10/21

## ChartData
DO NOT CHANGE ANYTHING IN THIS SHEET. IT AUTOMATICALLY PULLS DATA FROM THE 'EFFORT_RAW_DATA' SHEET.
Date | Me | Ideal | Forecast | Week
2021-02-03 | 106 | 106 | 106 | 1
2021-02-10 | 100.5 | 97.1667 | 100.5 | 2
2021-02-17 | 87 | 88.3333 | 87 | 3
2021-02-24 | 65 | 79.5 | 65 | 4
2021-03-03 | 65 | 70.6667 | 54.75 | 5
2021-03-10 | 65 | 61.8333 | 44.5 | 6
2021-03-17 | 65 | 53 | 34.25 | 7
2021-03-24 | 65 | 44.1667 | 24 | 8
2021-03-31 | 65 | 35.3333 | 13.75 | 9
2021-04-07 | 65 | 26.5 | 3.5 | 10
2021-04-14 | 65 | 17.6667 | 0 | 11
2021-04-21 | 65 | 8.8333 | 0 | 12
2021-04-28 | 65 | 0 | 0 | 13